## START HERE
SECURITY RISK QUANTIFICATION MODEL
Navigation Guide — Start here. Follow the workflow left to right.
1 | Assumptions · SET ONCE
Configure your org's financial context — revenue, insurance coverage, risk appetite threshold, and severity-to-dollar mappings. Everything else derives from these inputs.
2 | Issue Intake · WHEN NEW FINDINGS ARRIVE
Paste raw findings from any scanner, audit, or pentest. Use the normalization guide to map to structured financial inputs. ALE, Residual ALE, and ROSI auto-calculate. Mark 'Yes' to transfer to Issue Register.
3 | Issue Register · ONGOING — SOURCE OF TRUTH
The master log of all issues. Each row is one issue with full financial context. Update Status (Open / In Remediation / Closed) and dates as issues progress. All other tabs pull from here.
4 | Priority Ranking · WEEKLY — OPERATIONAL
All open issues ranked by ROSI (financial return per remediation dollar). Shows Priority Tier, Days Open, and Recommended Action. Sprint Planning view surfaces your top 5 highest-return fixes.
5 | Risk Domain Heat Map · MONTHLY — ANALYTICAL
Domain-level ALE rollup and 5×5 likelihood/impact grid. Use to identify which security domains carry the most financial exposure and where to concentrate program investment.
6 | Monthly Dashboard · MONTHLY — BOARD / EXEC
Board and Risk Committee reporting view. Monthly pipeline table, KPI scorecard with RAG status, and pre-drafted narrative block. Portfolio ALE and ROSI KPIs update automatically.
7 | ROSI & Prioritization · CALCULATION ENGINE
Raw ROSI ranking data that feeds the Priority Ranking tab. Do not delete. Refer to Priority Ranking for the full prioritization view.
Workflow: Assumptions → Issue Intake → Issue Register → Priority Ranking → Heat Map → Monthly Dashboard

## Issue Intake
SECURITY ISSUE INTAKE — RAW FINDING NORMALIZER
Paste raw findings from any scanner, audit, or manual review. Map each to structured financial inputs. Blue cells = your inputs. Black cells = auto-calculated. Use Issue ID to link to Issue Register.
A. NORMALIZATION REFERENCE — Mapping Raw Finding Language to Structured Inputs
Raw Finding Type |  | Example Language |  | Risk Domain |  | Suggested Severity |  | Typical Threat Frequency (annual) |  | Typical Vulnerability Prob. |  | Calibration Note
Vulnerability Scanner (Nessus/Qualys/Tenable) |  | Critical: Remote code execution CVE-2024-XXXXX on internet-facing host |  | Infrastructure |  | Critical |  | 0.7 – 0.9 (internet-facing) |  | 0.8 – 0.95 |  | Use CVSS exploitability score as proxy for Vuln Prob. EPSS score if available.
Cloud Posture (CSPM / Security Hub) |  | S3 bucket with public access enabled, contains PII |  | Data Protection |  | High |  | 0.5 – 0.7 (opportunistic scan) |  | 0.6 – 0.8 |  | Frequency = likelihood of opportunistic attacker finding misconfiguration. Loss magnitude = data classification × records exposed.
Identity Audit (IAM / AD Review) |  | Privileged accounts without MFA — 47 accounts |  | Identity & Access |  | High |  | 0.6 – 0.8 (credential attacks) |  | 0.7 – 0.85 |  | Scale ALE by account count × avg privilege level. Admin accounts 3–5× standard user ALE.
Penetration Test (Manual) |  | SQL injection in authenticated customer portal — High severity |  | Application |  | Critical |  | 0.3 – 0.6 (targeted attack) |  | 0.7 – 0.9 |  | Pentest findings = confirmed vulnerability. Set Vuln Prob at high end. Loss magnitude includes breach notification, regulatory fines.
Compliance / Audit (SOC 2 / ISO gap) |  | No formal vendor risk assessment process — control gap |  | Third-Party Risk |  | Medium |  | 0.2 – 0.4 (indirect via vendor) |  | 0.4 – 0.6 |  | Compliance gaps = process risk, not technical exploit. Use conservative frequency. Loss = regulatory exposure + audit finding cost.
SIEM / Detection (Alert / Anomaly) |  | 30 endpoints not sending logs to SIEM — detection blind spot |  | Detection & Response |  | Medium–High |  | 0.3 – 0.5 (incident going undetected) |  | 0.5 – 0.7 |  | Model as: detection failure increases dwell time, which increases loss magnitude. Add dwell-time multiplier to base financial impact.
Patch Management (Patch Gap) |  | Windows Server — critical patch 45 days overdue (CVE-2024-38124) |  | Infrastructure |  | Critical |  | 0.6 – 0.85 (known exploit in wild) |  | 0.85 – 0.95 |  | Check CISA KEV list for active exploitation. If on KEV, set frequency at 0.85+. Days-exposed increases Vuln Prob over time.
B. ISSUE INTAKE FORM — Enter Raw Findings Below (one row per issue)
Issue ID (auto or manual) | Raw Finding Text (paste as-is from scanner/audit) | Source Tool / Scanner | Date Found | Proposed Risk Domain | Proposed Severity (C/H/M/L) | Asset Value at Risk ($) | Threat Freq. (annual, 0–1) | Vulnerability Prob. (0–1) | Existing Control Factor (0=none, 1=full) | Est. Remediation Cost ($) | ALE ($) [auto] | Residual ALE ($) [auto] | ROSI [auto] | Priority Score [auto] | Transfer to Issue Register?
TOTALS | [10 empty] | 0 | 0 |  | 0
C. CALIBRATION TIPS — How to Set Threat Frequency and Vulnerability Probability from Real Data
Threat Frequency |  |  | SIEM data: count credential-based alert events over 90 days → annualize. Verizon DBIR: industry-specific breach frequency rates. CISA KEV: if CVE is on KEV list, set frequency ≥ 0.7.
Vulnerability Probability |  |  | CVSS exploitability sub-score ÷ 10 as starting point. EPSS score (empirical probability of exploitation within 30 days) × 12 for annual. Pentest finding = confirmed → set 0.8+. Scanner finding = potential → set 0.4–0.6.
Asset Value at Risk |  |  | Revenue at risk per system: Annual Revenue ÷ 8,760 hrs × Max Downtime hrs. Data breach cost: records × avg cost per record ($150–$250 per Ponemon). Regulatory fine exposure: GDPR up to 4% global revenue; HIPAA up to $1.9M per violation category.
Control Effectiveness Factor |  |  | 0.0 = No controls in place (full ALE). 0.25 = Strong compensating controls (residual 25% of raw ALE). 0.5 = Partial controls. 0.75 = Minimal controls. Source: NIST SP 800-53 control effectiveness ratings; CIS Control implementation groups.

## Issue Register
SECURITY ISSUE REGISTER — RISK QUANTIFICATION
Source of truth for all security issues. Each row is one issue. Blue = input. Black = calculated. Update status/dates as issues progress.
Issue ID | Issue Description | Source / Scanner | Date Ingested | Target Remediation Date | Date Closed | Status | Risk Domain | Raw Severity (C/H/M/L) | Numeric Severity Score | Likelihood Score | Control Effective. Factor | Risk Score (Calculated) | Residual Risk Score | Base Financial Impact ($) | Probability of Exploit | ALE ($) (Annual) | Remediation Cost ($) | ROSI
SEC-001 | Unpatched critical RCE in internet-facing web app | Tenable / Nessus | 2024-10-03 | 2024-10-17 |  | Open | Infrastructure | Critical | 10 | 0.9 | 0.85 | 7.65 | 5.6993 | 250000 | 90% | 225000 | 25000 | 8
SEC-002 | Default credentials on network device (firewall) | Manual Pentest | 2024-10-05 | 2024-10-12 | 2024-10-15 | Closed | Network | Critical | 10 | 0.9 | 0.9 | 8.1 | 5.913 | 250000 | 90% | 225000 | 30000 | 6.5
SEC-003 | Sensitive PII stored unencrypted in S3 bucket | Cloud Security Posture | 2024-10-08 | 2024-10-31 |  | Open | Data Protection | High | 7 | 0.65 | 0.7 | 3.185 | 2.5162 | 1500000 | 65% | 975000 | 45000 | 20.6667
SEC-004 | MFA not enforced for privileged admin accounts | Identity Audit | 2024-10-10 | 2024-10-24 | 2024-10-28 | Closed | Identity & Access | High | 7 | 0.65 | 0.75 | 3.4125 | 2.6447 | 1500000 | 65% | 975000 | 18000 | 53.1667
SEC-005 | Outdated TLS 1.0 on internal API gateway | Qualys | 2024-10-12 | 2024-11-15 |  | Open | Network | High | 7 | 0.65 | 0.6 | 2.73 | 2.2386 | 1500000 | 65% | 975000 | 22000 | 43.3182
SEC-006 | SQL injection vulnerability in customer portal | DAST / Burp | 2024-10-15 | 2024-10-29 |  | In Remediation | Application | Critical | 10 | 0.9 | 0.8 | 7.2 | 5.472 | 5000000 | 90% | 4500000 | 65000 | 68.2308
SEC-007 | Missing security headers on marketing website | Web Scan | 2024-10-18 | 2024-11-30 |  | Open | Application | Low | 2 | 0.1 | 0.3 | 0.06 | 0.0546 | 75000 | 10% | 7500 | 5000 | 0.5
SEC-008 | Endpoint without EDR agent (30 devices) | SIEM / Asset Inv. | 2024-10-20 | 2024-11-08 |  | Open | Endpoint | Medium | 4 | 0.35 | 0.55 | 0.77 | 0.64295 | 350000 | 35% | 122500 | 35000 | 2.5
SEC-009 | Stale privileged accounts (90+ days inactive) | AD Audit | 2024-10-22 | 2024-11-01 | 2024-11-05 | Closed | Identity & Access | Medium | 4 | 0.35 | 0.65 | 0.91 | 0.73255 | 350000 | 35% | 122500 | 8000 | 14.3125
SEC-010 | Insecure direct object reference in HR app | Code Review | 2024-10-25 | 2024-11-20 |  | Open | Application | High | 7 | 0.65 | 0.7 | 3.185 | 2.5162 | 1500000 | 65% | 975000 | 28000 | 33.8214
SEC-011 | Log ingestion gaps — 3 critical systems not in SIEM | SIEM Review | 2024-11-01 | 2024-11-22 |  | In Remediation | Detection & Response | 7 | 7 | 0.65 | 0.5 | 2.275 | 1.9338 | 1500000 | 65% | 975000 | 42000 | 22.2143
SEC-012 | Third-party vendor with excessive data access | Vendor Assessment | 2024-11-04 | 2024-11-30 |  | Open | Third-Party Risk | High | 7 | 0.65 | 0.6 | 2.73 | 2.2386 | 1500000 | 65% | 975000 | 15000 | 64
SEC-013 | Missing patch — Windows Server 2019 (CVE-2024-38124) | Patch Mgmt | 2024-11-06 | 2024-11-13 | 2024-11-12 | Closed | Infrastructure | Critical | 10 | 0.9 | 0.9 | 8.1 | 5.913 | 5000000 | 90% | 4500000 | 12000 | 374
SEC-014 | DLP not configured for outbound email | DLP Policy Review | 2024-11-08 | 2024-12-15 |  | Open | Data Protection | Medium | 4 | 0.35 | 0.45 | 0.63 | 0.54495 | 350000 | 35% | 122500 | 55000 | 1.2273
SEC-015 | Container images with known HIGH CVEs in prod | Container Scan | 2024-11-10 | 2024-11-24 |  | Open | Infrastructure | High | 7 | 0.65 | 0.65 | 2.9575 | 2.3808 | 1500000 | 65% | 975000 | 32000 | 29.4688
TOTALS / PORTFOLIO SUMMARY | [8 empty] | 6.8667 | 0.62 | 0.66 | 3.593 | 2.7627 | 22125000 | 0.62 | 16650000 | 437000

## Priority Ranking
SECURITY ISSUE PRIORITIZATION ENGINE — RANKED BY FINANCIAL IMPACT PER REMEDIATION DOLLAR
All open issues from the Issue Register, ranked by ROSI descending. Highest-return remediations at the top. Color bands show priority tier. Use this view to build your remediation sprint plan.
A. PORTFOLIO SUMMARY — Current Open Issues
Total Open Issues |  | Total Portfolio ALE ($) |  | Total Remediation Budget Needed ($) |  | Avg ROSI (open issues) |  | Issues Above Risk Appetite |  | Est. ALE Reduction if Top 5 Fixed
11 |  | 10827500 |  | 369000 |  | 22.6114 |  | 0 |  | 3900000
B. PRIORITY TIER LEGEND
Tier |  | Color Code |  | ROSI / ALE Threshold |  | Recommended Action
TIER 1 — IMMEDIATE |  | ● |  | ROSI > 20x OR ALE > $2M |  | Fix within 7 days. No budget conversation needed.
TIER 2 — HIGH PRIORITY |  | ● |  | ROSI 10x–20x OR ALE $500K–$2M |  | Fix within 30 days. Include in next sprint.
TIER 3 — STANDARD |  | ● |  | ROSI 3x–10x OR ALE $100K–$500K |  | Fix within 90 days. Schedule in roadmap.
TIER 4 — MONITOR |  | ● |  | ROSI 1x–3x OR ALE < $100K |  | Fix when capacity allows. Consider risk acceptance.
TIER 5 — DEPRIORITIZE |  | ● |  | ROSI < 1x |  | Cost exceeds benefit. Formally accept or transfer risk.
C. RANKED REMEDIATION BACKLOG — All Open Issues Sorted by Financial Priority
Priority Rank | Issue ID | Description | Risk Domain | Severity | Status | ALE ($) | Remediation Cost ($) | Risk Reduction % | Financial Benefit ($) | ROSI | Priority Tier | Days Open | Recommended Action
REMEDIATION PRIORITIZATION — RANKED BY FINANCIAL RISK REDUCTION
2 | Issue ID | Description | Risk Domain | Severity | Status | ALE ($) | Remediation Cost ($) | Risk Reduction Expected | Financial Benefit ($) | ROSI | TIER 1 — IMMEDIATE |  | Immediate — no budget gate
3 | SEC-001 | Unpatched RCE - Web App | Infrastructure | Critical | Open | 4500000 | 25000 | 90% | 4050000 | 161 | TIER 1 — IMMEDIATE | 597 | Immediate — no budget gate
4 | SEC-006 | SQL Injection - Customer Portal | Application | Critical | In Remediation | 4500000 | 65000 | 85% | 3825000 | 57.8462 | TIER 1 — IMMEDIATE | 585 | Immediate — no budget gate
5 | SEC-012 | Vendor Excessive Data Access | Third-Party Risk | High | Open | 975000 | 15000 | 60% | 585000 | 38 | TIER 1 — IMMEDIATE | 565 | Immediate — no budget gate
6 | SEC-005 | TLS 1.0 on API Gateway | Network | High | Open | 975000 | 22000 | 65% | 633750 | 27.8068 | TIER 1 — IMMEDIATE | 588 | Immediate — no budget gate
7 | SEC-010 | IDOR in HR Application | Application | High | Open | 975000 | 28000 | 75% | 731250 | 25.1161 | TIER 1 — IMMEDIATE | 575 | Immediate — no budget gate
8 | SEC-015 | Container CVEs in Production | Infrastructure | High | Open | 975000 | 32000 | 70% | 682500 | 20.3281 | TIER 1 — IMMEDIATE | 559 | Immediate — no budget gate
9 | SEC-003 | PII in Unencrypted S3 | Data Protection | High | Open | 975000 | 45000 | 80% | 780000 | 16.3333 | TIER 2 — HIGH PRIORITY | 592 | Fix within 30 days
10 | SEC-011 | SIEM Log Gaps | Detection & Response | High | In Remediation | 975000 | 42000 | 60% | 585000 | 12.9286 | TIER 2 — HIGH PRIORITY | 568 | Fix within 30 days
11 | SEC-008 | Endpoints without EDR | Endpoint | Medium | Open | 122500 | 35000 | 80% | 98000 | 1.8 | TIER 4 — MONITOR | 580 | Accept or transfer risk
12 | SEC-014 | DLP Not Configured | Data Protection | Medium | Open | 122500 | 55000 | 75% | 91875 | 0.67045 | TIER 5 — DEPRIORITIZE | 561 | Formally accept — deprioritize
13 | SEC-007 | Missing Security Headers | Application | Low | Open | 7500 | 5000 | 95% | 7125 | 0.425 | TIER 5 — DEPRIORITIZE | 582 | Formally accept — deprioritize
ROSI INTERPRETATION GUIDE & INVESTMENT RECOMMENDATION
17 | ROSI Band | Recommended Action
18 | ROSI > 10x | Exceptional — Immediate prioritization; funding should not be a barrier
19 | ROSI 5x–10x | Strong — High priority; include in next sprint/quarter budget
20 | ROSI 2x–5x | Good — Standard prioritization; schedule within risk appetite window
21 | ROSI 1x–2x | Marginal — Evaluate vs. risk transfer (insurance) or risk acceptance
22 | ROSI < 1x | Poor — Consider risk transfer, compensating controls, or formal acceptance
23 | Negative ROSI | Remediation cost exceeds expected ALE — formally accept or transfer risk
TOTALS (open issues only) | [5 empty] | 15102500 | 369000 |  | 12069500
D. SPRINT PLANNING VIEW — Top 5 Issues by Financial Priority
Sprint Rank | Issue ID | Description | ALE ($) | Rem. Cost ($) | ROSI | Financial Benefit ($) | Owner (assign) | Target Date | Notes
1 | REMEDIATION PRIORITIZATION — RANKED BY FINANCIAL RISK REDUCTION
2 | Issue ID | Description | ALE ($) | Remediation Cost ($) | ROSI | Financial Benefit ($)
3 | SEC-001 | Unpatched RCE - Web App | 4500000 | 25000 | 161 | 4050000
4 | SEC-006 | SQL Injection - Customer Portal | 4500000 | 65000 | 57.8462 | 3825000
5 | SEC-012 | Vendor Excessive Data Access | 975000 | 15000 | 38 | 585000
Formulas:
Days Open = IF([Issue ID]<>"",IFERROR(TODAY()-VLOOKUP([Issue ID],'Issue Register'!A:D,4,0),""),"")

## Risk Domain Heat Map
RISK DOMAIN HEAT MAP — ISSUE DISTRIBUTION & FINANCIAL EXPOSURE
ℹ Domain counts and ALE totals update automatically as issues are added to the Issue Register. RAG status is a manual judgment — update when domain posture changes.
Risk Domain | Total Issues | Critical | High | Medium | Low | Total ALE ($) | Avg Risk Score | Domain RAG
Application Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Red
Infrastructure | 3 | 2 | 1 | 0 | 0 | 5700000 | 6.2358 | Red
Identity & Access | 2 | 0 | 1 | 1 | 0 | 1097500 | 2.1612 | Amber
Data Protection | 2 | 0 | 1 | 1 | 0 | 1097500 | 1.9075 | Amber
Network Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Amber
Endpoint Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Green
Detection & Response | 1 | 0 | 0 | 0 | 0 | 975000 | 2.275 | Green
Third-Party Risk | 1 | 0 | 1 | 0 | 0 | 975000 | 2.73 | Green
PORTFOLIO TOTALS | 9 | 2 | 4 | 2 | 0 | 9845000 | 1.9137 | —
5×5 LIKELIHOOD × IMPACT HEAT MAP
← LIKELIHOOD / IMPACT → | Negligible <$100K | Minor $100K–$500K | Moderate $500K–$2M | Significant $2M–$10M | Catastrophic >$10M
Almost Certain (>75%) |  |  |  | SEC-001 | SEC-006
Likely (50–75%) |  |  | SEC-005,SEC-010 | SEC-003
Possible (25–50%) |  | SEC-014 | SEC-008,SEC-011
Unlikely (10–25%) | SEC-007 | SEC-012
Rare (<10%)
HEAT MAP LEGEND
Critical | High | Medium | Low

## Monthly Dashboard
SECURITY RISK PROGRAM — MONTHLY EXECUTIVE DASHBOARD
ℹ For operational issue triage, see → Issue Intake ¦ For ranked remediation backlog, see → Priority Ranking ¦ Portfolio ALE and ROSI KPIs on this tab update automatically from Issue Register.
Prepared for: Risk Committee / Board Reporting ¦ Frequency: Monthly ¦ Owner: CISO
MONTHLY ISSUE PIPELINE — FINANCIAL IMPACT SUMMARY
Month | Issues Ingested | Critical / High | Medium / Low | Issues Closed | Remaining Open | New Financial Exposure ($) | Closed Exposure ($) | Net Portfolio Exposure ($)
Aug 2024 | 8 | 3 | 5 | 5 | 3 | 11250000 | 4200000 | 7050000
Sep 2024 | 12 | 5 | 7 | 8 | 7 | 18750000 | 9100000 | 16700000
Oct 2024 | 11 | 6 | 5 | 5 | 13 | 17900000 | 6350000 | 28250000
Nov 2024 | 9 | 4 | 5 | 4 | 18 | 14800000 | 5200000 | 37850000
Dec 2024 | 6 | 2 | 4 | 3 | 21 | 8500000 | 3100000 | 43250000
Jan 2025 | 14 | 7 | 7 | 9 | 26 | 10827500 | 10200000 | 54550000
6-MONTH TOTAL | 46 | 20 | 26 | 25 | — | 71200000 | 27950000 | 133100000
CURRENT PERIOD KPI SCORECARD (JAN 2025)
KPI Metric | Target | Actual | Variance | RAG Status | Financial Context | Trend | Threshold (Board Alert) | Action Required
Mean Time to Remediate (Critical) | < 7 days | 5.2 days | -1.8 days | Green | Avg ALE avoided: $4.5M | ↑ Improving | > 14 days | None
Mean Time to Remediate (High) | < 30 days | 34 days | +4 days | Amber | Avg ALE exposed: $975K | → Stable | > 60 days | Escalate to CISO
Issues Ingested (month) | ≤ 10 | 14 | +4 | Amber | New ALE: $21.5M | ↓ Worsening | > 20 | Root cause review
Critical Issues Open > 7 days | 0 | 1 | +1 | Red | ALE at risk: $4.5M | ↓ Worsening | > 2 | Board notification
% Issues Closed On-Time | > 80% | 72% | -8% | Amber | SLA breach risk exposure | → Stable | < 50% | SLA review
Portfolio ALE (total open) | < $10M | 10827500 | +$11.5M | Red | Exceeds risk appetite | ↓ Worsening | > $25M | Risk Committee brief
ROSI (avg remediated issues) | > 3.0x | 22.6114 | +1.2x | Green | Strong control investment | ↑ Improving | < 1.5x | None
3rd Party Risk Issues Open | < 3 | 1 | -2 | Green | Vendor ALE: $975K | ↑ Improving | > 5 | None
BOARD / RISK COMMITTEE NARRATIVE — JANUARY 2025
Executive Summary: | In January 2025, the Security Risk Program ingested 14 new issues (7 Critical/High, 7 Medium/Low), closed 9 issues, and carries 21 open items. New financial exposure added this period totals $21.5M ALE. Closed issues reduced portfolio exposure by $10.2M. Net portfolio ALE stands at approximately $27.3M, exceeding our $10M risk appetite threshold — a Risk Committee discussion is required.
Critical Items: | 1 Critical issue (SQL injection — SEC-006) remains open beyond the 7-day SLA target, with estimated ALE of $4.5M. Remediation is in progress; ETA is 10 Feb 2025. No data exfiltration has been confirmed. SEC-013 (Windows Server CVE-2024-38124) was patched ahead of schedule — ALE of $4.5M mitigated.
Financial Impact: | Total remediation investment this period: $242K. Estimated ALE avoided through closed issues: $10.2M. Average ROSI across remediated issues: 4.2x — indicating strong return on security investment. Residual portfolio ALE above board alert threshold ($2M) requires formal acknowledgment.
Trend & Outlook: | Issue ingestion rate increased 56% vs. prior month, driven by a new cloud posture scan deployment. MTTR for Critical issues improved to 5.2 days (target: <7 days). Mean time for High issues at 34 days warrants attention. Forecast: issue volume expected to normalize by Feb-Mar 2025 as initial cloud scan backlog clears. Recommend prioritizing High-severity identity and data protection issues.
Recommended Actions: | 1. Risk Committee to formally accept or reject $27.3M portfolio ALE against $10M risk appetite. 2. Approve $65K remediation budget for SEC-006 SQL injection closure. 3. Request monthly update on High-severity MTTR improvement plan. 4. Note: SEC-012 (Vendor Data Access) approaching remediation deadline — vendor response pending.

## ROSI & Prioritization
⚠ CALCULATION ENGINE — This tab is the data source for the Priority Ranking tab. Do not delete or rename. For the full prioritization view with tier classification, sprint planning, and portfolio KPIs, see → Priority Ranking
ROSI ANALYSIS & REMEDIATION PRIORITIZATION MATRIX
REMEDIATION PRIORITIZATION — RANKED BY FINANCIAL RISK REDUCTION
Issue ID | Description | Severity | ALE ($) | Remediation Cost ($) | Risk Reduction Expected | Financial Benefit ($) | ROSI | Priority Rank
SEC-001 | Unpatched RCE - Web App | Critical | 4500000 | 25000 | 90% | 4050000 | 161 | #1
SEC-006 | SQL Injection - Customer Portal | Critical | 4500000 | 65000 | 85% | 3825000 | 57.8462 | #2
SEC-012 | Vendor Excessive Data Access | High | 975000 | 15000 | 60% | 585000 | 38 | #3
SEC-005 | TLS 1.0 on API Gateway | High | 975000 | 22000 | 65% | 633750 | 27.8068 | #4
SEC-010 | IDOR in HR Application | High | 975000 | 28000 | 75% | 731250 | 25.1161 | #5
SEC-015 | Container CVEs in Production | High | 975000 | 32000 | 70% | 682500 | 20.3281 | #6
SEC-003 | PII in Unencrypted S3 | High | 975000 | 45000 | 80% | 780000 | 16.3333 | #7
SEC-011 | SIEM Log Gaps | High | 975000 | 42000 | 60% | 585000 | 12.9286 | #8
SEC-008 | Endpoints without EDR | Medium | 122500 | 35000 | 80% | 98000 | 1.8 | #9
SEC-014 | DLP Not Configured | Medium | 122500 | 55000 | 75% | 91875 | 0.67045 | #10
SEC-007 | Missing Security Headers | Low | 7500 | 5000 | 95% | 7125 | 0.425 | #11
ROSI INTERPRETATION GUIDE & INVESTMENT RECOMMENDATION
ROSI Band | Recommended Action
ROSI > 10x | Exceptional — Immediate prioritization; funding should not be a barrier
ROSI 5x–10x | Strong — High priority; include in next sprint/quarter budget
ROSI 2x–5x | Good — Standard prioritization; schedule within risk appetite window
ROSI 1x–2x | Marginal — Evaluate vs. risk transfer (insurance) or risk acceptance
ROSI < 1x | Poor — Consider risk transfer, compensating controls, or formal acceptance
Negative ROSI | Remediation cost exceeds expected ALE — formally accept or transfer risk

## Assumptions
SECURITY RISK QUANTIFICATION MODEL — ASSUMPTIONS & SCORING GUIDE
All blue cells are user inputs. Black cells are calculated. Update assumptions to reflect your organization's risk appetite and financial context.
A. QUALITATIVE TO QUANTITATIVE SEVERITY MAPPING
Severity Rating | Numeric Score | Likelihood Score | Risk Score Range | Probability of Exploit (annual) | Base Financial Impact ($) | Impact Multiplier | Annualized Loss Expectancy (ALE)
Critical | 10 | 0.9 | 9.0 – 10.0 | 90% | 5000000 | 1.5 | 6750000
High | 7 | 0.65 | 6.5 – 8.9 | 65% | 1500000 | 1.25 | 1218750
Medium | 4 | 0.35 | 3.5 – 6.4 | 35% | 350000 | 1 | 122500
Low | 2 | 0.1 | 1.0 – 3.4 | 10% | 75000 | 0.75 | 5625
B. ORGANIZATIONAL FINANCIAL CONTEXT
Parameter | Value ($) | Notes
Annual Revenue ($) | 850000000
Cyber Insurance Coverage ($) | 25000000
Annual Security Budget ($) | 12000000
Max Tolerable Downtime (hrs) | 72
Revenue per Hour ($) | 97031.9635
Risk Appetite Threshold ($) | 5000000
Board Reporting Threshold ($) | 2000000
Exec Reporting Threshold ($) | 500000
C. RISK SCORING METHODOLOGY
Risk Score Formula: | Severity Score × Likelihood Score × Control Effectiveness Factor
Control Effectiveness: | 1.0 = No controls, 0.5 = Partial, 0.25 = Strong compensating controls
Residual Risk Score: | Risk Score × (1 − Control Effectiveness Reduction)
Financial Impact Formula: | Base Impact × Impact Multiplier × Probability of Exploit
ALE (Annualized Loss Exp.): | Financial Impact × Likelihood of occurrence in 12-month window
ROSI Formula: | (Risk Reduction × ALE) / Cost of Control